CJCC Meeting Minutes/ November 14th, 2022- 4pm

Joint Information Center

200 Bleckley Street, Anderson, SC 29625

Attendees: 19 (Who signed the sheet)

Carrie Skeen

George Ducworth

Brittany Senerius

Seth Riddley

Matthew Muth

Karen Bowen

Sgt. Nathan Mitchell

Vicki Redding

Auburn Callahan

Kathleen Suratt

Caden Smart

Theresa Thompson

Greg Shore

Don Brookshire

Sara Morell

Charlie Hall

Jennifer Johnson

Rev. Clark

Caroline Piaso

Minutes from October were approved

Case Management Review/Detention Center Population Committee Report

(Sergeant Nathan Mitchell Providing Update)

- 350 people in ACDC today (11/14/22)

- A lot of inmates have gone to prison

- The review board is really needing a representative from the Clerk of Court in the meetings

- When it comes to mental health evaluations:

  - Do the inmates have to be transported to Columbia?

  - Can we find or create something closer?

  - It is taxing on ACDC transport

Crisis Stabilization Committee

(Vicki Redding providing update)

- Northside location is looking promising

- The church board is having a meeting soon on if this location can be utilized

- Once we find a location, we can pin down the funding.

Mental Health Court, Grant’s and New Jail Update

(Carrie Skeen providing update)

- The new jail design meeting was held last week

- Demo of the structures where the new jail will be built has started today

- The rest of the old buildings will be removed in the next 8 weeks

  - General Schedule for New Jail

    - Schematic design complete 02/24/23

    - Design development completion 06/23/23

    - Construction documents 95%/Redi-check and final agency review 12/01/23

    - 100% construction documents/ready to bid 02/04/24

    - Bid/Award March 2024

    - Substantial completion: March 2026

- Showed graphic of the new jail

- Showed intercept graphic

- Anderson County may be getting some opioid money

Upstate Warriors Solution

(Theresa Thompson gave report)

- Veteran suicide prevention

- 50% of UWS connections are not connected to the VA

- Eligibility will serve 3rd of this amount

- Brittany Senerius asked if they are involved in DSS

  - For vulnerable adults

- Greg Shore said he would contact DHEC to help identify those who have committed suicide and are veterans

Mental Health and Veterans Court

- UWS feels strongly against having them separate because of veteran’s court mentoring process

  - If combined, they would lose mentoring connections

Next meeting December 12, 2022